## Tasks
Event: PEVC Symposium/Sumit
Leaders: Vivek, Joe, Francis
Date: April 17
Audience: more students with some professionals, SOM, Yale Grad Schools and other MBA schools
Estimated Attendance: not more than 350 - goal around 250
Location: Evans Hall
| Speakers | Oct 7th | 2014-11-06
x | Identify potential speakers | Bob Davis will send out invites | have all panel topics finalized
| Send potential speaker list to Adrienne Gallagher in Development |  | will share google doc with her
Extend invitations to speakers
Secure speaker commitments
Coordinate reimbursements with speakers for travel or accomidation
Aquire speaker gifts
if event in in Evans Hall - send all speaker names and event agenda to SOM Front desk
consider transportation for speakers (and guests) to and from hotels and Union Station
Reach out to the Deans office to inqure about Deans participation
Sponsorship
| Identify potential sponsors | SOMAA | have been putting it together
Send potential sponsor list to Adrienne Gallagher in Development
Reach out to sponsors
Secure sponsor commitments
Logistics
x | Select a date
| Create a leadership team with defined roles | need to do next | about to finalize
x | Secure space |  | will have lunch at lawn club
secure parking
x | create an event agenda |  | done
finalize event agenda
arrange custodial set ups for sessions
arrange custodial set ups for registration
arrange custodial set ups for meals
Order catering
request necessecary AV support
| Registrations and Marketing |  | want to prevent to much providers
| Develop an event theme and title | general theme - challenges to the industry and challenges going forward, need a tagline
| Create an event website | have the link need to update it | will outsource
Create an event specific logo - approved by Ben Mattison in Communications
| Determine registration options and pricing structure | have references | will charge students - one for SOM, one external, higher price for non-Students
| create a registration system |  | start of January is the goal for registration to open
create a marketing plan
send a save the date
x | work with SOMAA for alumni marketing and inolvement |  | done
send initial invitation with registration
send follow up invitation with registration
send final invitation with registration
Materials
Design any custom give aways and have approved by Communications
Order custom materials
Order non-custom materials
Desgin brochures - approved by Communiactions
Order brohures
Design signage
Order signage
Arrange use of stanchions or easles
Arrange space for material preperation and storage leading up to the event
Budget
in progress | create an initial budget | lunch will be the most expensive
Create a detailed budget
meet with Mary Ann Green in AASL to review reimbursement, payment processes
Notes: | Sumit Structure - allow forum for discussion, student learning | just met with advisory board | pre christamas goals: Asks for sponsorship and speakers marketing plan website custom branding
Shark Tank - first round at Closing Bell, finals at Conference

## Timeline
12-7 Months in Advance | 2014-09-17 | Select a date | x
|  | Create a leadership team with defined roles | 0
|  | Secure space | x
|  | Identify potential speakers | x
|  | Identify potential sponsors | 0
6 Months in Advance | 2014-10-17 | Send potential speaker list to Adrienne Gallagher in Development | 0
|  | Send potential sponsor list to Adrienne Gallagher in Development | 0
|  | Develop an event theme and title | 0
|  | create an initial budget | in progress
|  | create a marketing plan | 0
5 Months in Advance | 2014-11-17 | Extend invitations to speakers | 0
|  | Reach out to sponsors | 0
|  | Create an event website | 0
|  | Create an event specific logo - approved by Ben Mattison in Communications | 0
|  | work with SOMAA for alumni marketing and inolvement | x
|  | Determine registration options and pricing structure | 0
4 Months in Advance | 2014-12-17 | Secure sponsor commitments | 0
|  | Secure speaker commitments | 0
|  | Create a detailed budget | 0
|  | Reach out to the Deans office to inqure about Deans participation | 0
|  | send a save the date | 0
3 Months in Advance | 2014-01-17 | create an event agenda | x
|  | create a registration system | 0
|  | Desgin brochures - approved by Communiactions | 0
|  | Design any custom give aways and have approved by Communications | 0
|  | send initial invitation with registration | 0
|  | Design signage | 0
2 Months in Advance | 2014-02-17 | secure parking | 0
|  | arrange custodial set ups for sessions | 0
|  | arrange custodial set ups for registration | 0
|  | arrange custodial set ups for meals | 0
|  | Arrange use of stanchions or easles | 0
|  | Arrange space for material preperation and storage leading up to the event | 0
|  | request necessecary AV support | 0
|  | Coordinate reimbursements with speakers for travel or accomidation | 0
|  | Order custom materials | 0
|  | Order signage | 0
|  | finalize event agenda | 0
|  | Order brohures | 0
|  | Order non-custom materials | 0
|  | Aquire speaker gifts | 0
|  | send follow up invitation with registration | 0
|  | send final invitation with registration | 0
1 Month in Advance | 2014-03-17 | Order catering | 0
|  | meet with Mary Ann Green in AASL to review reimbursement, payment processes | 0
|  | if event in in Evans Hall - send all speaker names and event agenda to SOM Front desk | 0
|  | consider transportation for speakers (and guests) to and from hotels and Union Station | 0
Post Event |  | Send Thank you Notes
Complete Conference debrief form and meeting with AASL
submit all outstanding invoices and request for Reimbursement